## October
Server: | PNMML-SVR | Database: | Monitoring | System: | Monitoring
Date From : | Oct 01 2018
Date To: | Oct 27 2018
Day | Effected Form/ SP |  | Problem/Issue |  |  | Fix Description/Develop/Functions
Monday | Email Sender.vb |  |  |  |  | Create a new program to send email.
| Proxy.vb |  |  |  |  | add new function to send mutiple email
| Entry.aspx |  |  |  |  | Add Image if data not found.
add timer for real time web page.
add new column named "SEND" to monitor if schedule has been sent through "EMAIL SENDER.vb"
Tuesday | EmailSender |  |  |  |  | change my script to conding standard.
| sp_monitoring_Select |  |  |  |  | continue email sender
| Entry.aspx |  |  |  |  | create new web page naming Login.aspx
change popup message
Wednesday | EmailSender |  |  |  |  | send to multiple email accounts
| Calendar.aspx |  |  |  |  | Calendar Design
Thursday | Entry.aspx |  |  |  |  | add gylphicon on buttons
| Email Sender.vb |  |  |  |  | add condition if SQL Commnad is for reset and change password.
| sp_Monitor_update |  |  |  |  | Create Login and user defined if not officer or admin.
Friday | Login.aspx.vb |  |  |  |  | develop a new condition if Password and BioCode column are equal automatic show Modal to force change user password.
| sp_monitoring_select |  |  |  |  | create new prodecure for tempolary table to eliminate empty records.
Entry.aspx
sp_monitoring_Temp
Saturday | Email Sender.vb |  |  |  |  | add function to checks date tomorrow
add new function for errors handling
Day | Effected Form/ SP |  | Problem/Issue |  |  | Fix Description/Develop/Functions
Monday | Email Sender.vb |  |  |  |  | ~>continue develop on real time sending, including on this development is email output to sent Calls and Visitors for all officers according by Date and OfficerID.
Proxy.vb
Tuesday | EmailSender.vb |  |  |  |  | ~>change database structure and coding structure included :
| sp_monitoring_Select |  |  |  |  | ~>all stored procedures are revision especially in sp_Monitoring_select first I can do is select all records for visitor table to monitor table with counting all
records then insert in temporary table named #TempVisitors.
Wednesday | sp_monitoring_Select |  | System Revision |  |  | ~>continued query revision on load records,
| sp_monitoring_insert |  |  |  |  | ~>including revision is for updating records first I can do is to check records according to RowID and MonitorID for table Calls to check if command
| sp_monitoring_update |  |  |  |  | is for update or insert.
sp_monitoring_delete
sp_monitoring_Temp
Thursday | sp_monitoring_Select |  |  |  |  | ~>continued query revision for update records and load records
| sp_monitoring_update |  |  |  |  | ~>on deleting records "sp_monitor_delete" add condition if records for Calls is not existing and Visitor Table start command to delete records in Monitor table,
| sp_monitoring_delete |  |  |  |  | in this way to eliminate multiple records for one officer.
Friday | EmailSender.vb |  |  |  |  | ~>Hold project for Email Sender I'll mention this project is for real time sending.
| sp_monitoring_Select |  |  |  |  | ~> including my revision in Client Side, such as sending parameter to store procedure for example parameter named @column set by two columns and ordering,
| Calendar.aspx |  |  |  |  | now I set for only ordering which is DESCENDING OR ASCENDING.
| sp_monitoing_delete |  |  |  |  | ~>add button to manual sending email exclusive for one officer to eliminate running programs on server.
Saturday | sp_monitoring_delete |  |  |  |  | ~>continue query revision on updating records
| Calendar.aspx |  |  |  |  | ~>continue develop in manual Email sending.
~>add Modal Message if succesful sent via Email to notified admin user the status of sending if passed or failed.
Day | Effected Form/ SP |  | Problem/Issue |  |  | Fix Description/Develop/Functions
Monday | Calendar.aspx |  |  |  |  | ~> continue developing on Manual Sending,
| sp_Monitor_Update |  |  |  |  | ~>add condition to Visible Button Email Sender to reduce multiple sending by admin user.
| sp_Monitor_Select |  |  |  |  | ~>add column named "Email" in table Visitor and Calls, to verified if Email succesful sent or not.
~>add column named "Amended" in table Visitor and Calls if schedule has been updated.
Tuesday | Calendar.aspx |  |  |  |  | ~>continue develeping on Manual Sending
| sp_Monitor_Update |  |  |  |  | ~>add new condition if schedule is not sent to Officer's Email and not updated by admin the word AMENDED is not show .
~> Application Testing
Wednesday | Calendar.aspx |  | invalid output of Officer name on calendar view and count for Visitors |  |  | ~>continue Application Testing
| sp_Monitor_select |  |  |  |  | ~>create a new temporay table contain all result by current month and ordering by date to descending.
Thursday | Entry.aspx |  | System Revision on data entry including delete and updating records |  |  | ~>system revision especially user interface, even selecting records to fill-out in the main data gridview. Including deleting records if Call's or Visitor's RowID
| sp_Monitor_Delete |  |  |  |  | ~>even deleting records if Monitor , Calls or Visitors are empty.
| sp_Monitor_View |  |  |  |  | ~>create procedure to select all records exclusing for Visitor and Calls according by date and Officer Name for once the admin add new records.
sp_Monitor_select
Friday | sp_Monitor_Update |  |  |  |  | ~>continue system enhancement including user interface and functions
| sp_Monitor_Insert |  |  |  |  | ~>add column in Monitor Table named EditedID the purpose of this column is to know who the last updater of the schedule.
sp_Monitor_Select
Entry.aspx
Saturday | sp_Monitor_Update |  |  |  |  | ~>separate Modal Message to all pop-up message to alert system user.
| sp_Monitor_Insert |  |  |  |  | ~> Application Testing.
Entry.aspx
Day | Effected Form/ SP |  | Problem/Issue |  |  | Fix Description/Develop/Functions
Monday | Calendar.aspx |  |  |  |  | ~>Application Testing and find the posible errors.
Entry.aspx
Server: | PNMML-SVR / SVMML-SVR | Database: | SV-MML / PN-MML | System: | Purchase Book / Accounting _SV
Tuesday | sp_Report_Ledger_Listing_Summary |  |  |  |  | ~>Analyst and understand the coding standard and also how to get beginning balance, subTotal Per Month and subTotal Per Account
sp_Report_Ledger_Listing
Wednesday | sp_Report_Ledger_Listing_Summary |  |  |  |  | ~>Continue analyst and understand what table used on this Procedures especially in Purchase Book
sp_Report_Ledger_Listing
Thursday | sp_BO_DRIN_Detail_SI_Update |  |  |  |  | ~>Study system flow and understand how to compute the total Cost per product
sp_BO_DRIN_Header_PrepaidInput_Update
sp_BO_DRIN_Header_SI_Update
SI System
Friday | sp_BO_DRIN_Detail_SI_Update |  |  |  |  | ~>Continue analyst the system flow chart.
sp_BO_DRIN_Header_PrepaidInput_Update
sp_BO_DRIN_Header_SI_Update
SI System
Saturday | sp_BO_DRIN_Detail_SI_Update |  |  |  |  | ~>Continue understanding the system flow chart
sp_BO_DRIN_Header_PrepaidInput_Update
sp_BO_DRIN_Header_SI_Update
SI System
Server: | PNMML-SVR / SVMML-SVR | Database: | SV-MML / PN-MML | System: | Purchase Book / Accounting _SV
Tuesday
Wednesday
Thursday
Friday
Saturday